## Instructions
NIST RMF Authorization Toolkit
Companion workbook to the NIST RMF Authorization Handbook (.docx) - reusable templates for every step of the 7-step RMF ATO lifecycle.
How to use this workbook
1. | This workbook contains 11 templates (Template 1-11), one per tab, each paired with a numbered walkthrough in Part Four of the companion handbook.
2. | Work through the tabs roughly in RMF step order (Prepare -> Categorize -> Select -> Implement -> Assess -> Authorize -> Monitor) on your first authorization package. On future packages, start from Template 1 and jump to whichever tabs you need.
3. | Every template includes one example row in gray italics near the top - read it, then delete it or leave it for reference and add your own rows below.
4. | White-headed columns marked 'Reference' are pre-populated reference content (control families, step descriptions, assessment procedure summaries) - do not delete these, only add to them if SP 800-53/SP 800-37 is updated.
5. | Cells with a dropdown arrow use validated lists (e.g. Satisfied/Other Than Satisfied, Authorized/Denied) - use the dropdown rather than typing free text, so future filtering and reporting stays consistent.
6. | Duplicate this whole workbook file at the start of each new system's authorization package (e.g. 'NIST RMF Authorization Toolkit - System XYZ - Initial ATO.xlsx') so you keep a clean, dated record per system.
7. | This is NOT a one-time certification kit: RMF is a continuous lifecycle. Template 11 (Continuous Monitoring Schedule) and Template 8 (POA&M) are meant to persist and be updated throughout the system's operational life, not just at initial authorization.
8. | This toolkit reflects agency-internal RMF as described in NIST SP 800-37 Rev 2. If you are supporting a FedRAMP cloud authorization instead, see the 'If You're Pursuing FedRAMP Instead of Agency-Internal RMF' sidebar in Part Three of the handbook - the same templates apply, but the assessor role must be filled by an accredited 3PAO.
Tab index
Tab name | Purpose
Template 1 - RMF Project Plan | Prepare step: roles assigned, risk strategy, common controls, ConMon strategy outline.
Template 2 - Categorization Worksheet | Categorize step: FIPS 199 impact levels (C/I/A) and overall system categorization.
Template 3 - Control Selection | Select step: baseline selection and tailoring, organized by the 20 SP 800-53 families.
Template 4 - Implementation Tracker | Implement step: control-by-control implementation status.
Template 5 - SAP Worksheet | Assess step: Security Assessment Plan - scope, methods, schedule, team.
Template 6 - Control Assessment | Assess step: control-by-control test results organized by the 20 families.
Template 7 - Evidence Log | Assess step: chronological record of every piece of evidence examined.
Template 8 - POA&M | Assess/Monitor steps: Plan of Action and Milestones - tracks remediation of weaknesses.
Template 9 - SAR Summary | Assess step: Security Assessment Report summary for the authorization package.
Template 10 - Authorization Decision | Authorize step: the AO's non-delegable risk-acceptance decision record.
Template 11 - ConMon Schedule | Monitor step: ongoing monitoring cadence per control/family, supporting ongoing authorization.
The 7 RMF steps at a glance
Step | Key output
1. Prepare | Roles defined, risk strategy set, common-control inventory
2. Categorize | System categorized Low/Moderate/High per security objective
3. Select | System Security (and Privacy) Plan (SSP)
4. Implement | Controls deployed; SSP updated to as-implemented state
5. Assess | Security Assessment Plan (SAP), Security Assessment Report (SAR), initial POA&M
6. Authorize | Authorization decision document - status (ATO / Authorized to Use / Denial), terms/conditions, termination date
7. Monitor | Updated risk posture, POA&M updates, possible reauthorization

## Template 1 - RMF Project Plan
Template 1 - RMF Project Plan (Prepare Step)
Establish roles, risk strategy, common controls and the ConMon approach before categorization begins. See Handbook Walkthrough A.
System Name | Case Management Portal (EXAMPLE)
System Owner | R. Alvarez, Program Director (EXAMPLE)
Authorizing Official (AO) | D. Whitfield, CISO (EXAMPLE)
AO Designated Representative (AODR), if any | K. Osei (EXAMPLE)
ISSO / System Security Officer | P. Nakamura (EXAMPLE)
Common Control Provider(s) | Agency Enterprise Infrastructure Team - network boundary, physical security (EXAMPLE)
Control Assessor / SCA (organizationally independent of System Owner) | Independent Assessment Team, Agency Office of IG (EXAMPLE)
Organizational Risk Tolerance Statement | Agency accepts Low residual risk without conditions; Moderate residual risk requires AO conditions and POA&M; High residual risk requires remediation before ATO (EXAMPLE)
Mission / Business Process Supported | Public benefits case intake and adjudication (EXAMPLE)
Common Controls Identified (inherited, not to be reassessed at system level) | Physical/environmental controls (PE family) inherited from agency data center; network boundary protection (SC-7) inherited from enterprise perimeter (EXAMPLE)
Continuous Monitoring (ConMon) Strategy Outline | Automated vulnerability scanning weekly; access reviews quarterly; full control reassessment on 3-year cycle or significant change, whichever comes first (EXAMPLE)
Organization-wide Risk Assessment Reference (SP 800-39/800-30) | Agency Enterprise Risk Assessment, FY2026, ref ERA-2026-01 (EXAMPLE)
Prepare-step task checklist
Task | Status | Owner | Notes
Identify and document key risk-management roles (AO, System Owner, ISSO, Control Assessor, Common Control Provider) | Complete (EXAMPLE) | D. Whitfield | Roles confirmed via appointment memo dated 2026-01-15 (EXAMPLE)
Establish/confirm organizational risk management strategy and risk tolerance
Conduct or reference the organization-wide risk assessment
Identify common controls available for inheritance
Develop the organizational and system-level continuous monitoring (ConMon) strategy
Identify the mission/business process(es) the system supports

## Template 2 - Categorization
Template 2 - System Categorization Worksheet (Categorize Step)
Determine FIPS 199 impact levels and overall system categorization. See Handbook Walkthrough B.
System Name | Case Management Portal (EXAMPLE)
System Description | Web application supporting intake, review and adjudication of public benefits cases; processes PII (EXAMPLE)
Information Types (per SP 800-60 Vol II) | Public benefits case data; personally identifiable information (PII) (EXAMPLE)
FIPS 199 impact determination
Security Objective | Definition (loss of...) | Potential Impact Level | Rationale | Approved By (AO)
Confidentiality | Unauthorized disclosure of information | Moderate (EXAMPLE) | PII disclosure would cause serious adverse effect on individuals, but not catastrophic (EXAMPLE) | D. Whitfield (EXAMPLE)
Integrity | Unauthorized modification/destruction of information | Moderate
Availability | Disruption of access to or use of information/system | Low
Overall System Categorization (high-water mark) | Moderate (EXAMPLE - determined by the highest of the three ratings above)
AO Review and Approval of Categorization
AO Name / Signature |  | Date

## Template 3 - Control Selection
Template 3 - Control Selection & Tailoring Worksheet (Select Step)
Select the baseline per system categorization, tailor, and designate control implementation type. See Handbook Walkthrough C.
Family | Family Name (Reference) | Baseline Control | Baseline (L/M/H) | Tailoring Decision / Rationale | Implementation Type | Selected For Baseline (Y/N)
AC | Access Control | AC-2 Account Management | Moderate | Baseline control retained as-is; no tailoring applied (EXAMPLE) | System-Specific | Y
AC | Access Control
AT | Awareness and Training
AU | Audit and Accountability
CA | Assessment, Authorization, and Monitoring
CM | Configuration Management
CP | Contingency Planning
IA | Identification and Authentication
IR | Incident Response
MA | Maintenance
MP | Media Protection
PE | Physical and Environmental Protection
PL | Planning
PM | Program Management
PS | Personnel Security
PT | PII Processing and Transparency
RA | Risk Assessment
SA | System and Services Acquisition
SC | System and Communications Protection
SI | System and Information Integrity
SR | Supply Chain Risk Management

## Template 4 - Implementation
Template 4 - Implementation Tracker (Implement Step)
Track control-by-control implementation status as the SSP moves from planned to as-implemented. See Handbook Walkthrough D.
Control ID | Family | Control Name | Implementation Description | Status | Responsible Party | Target Date | SSP Updated (Y/N)
AC-2 | AC | Account Management | Automated account provisioning/deprovisioning implemented via IAM platform integrated with HR feed (EXAMPLE) | Implemented | P. Nakamura (ISSO) | 2026-04-01 | Y
AC-1 | AC | Policy and Procedures
AC-2 | AC | Account Management
AC-3 | AC | Access Enforcement
AC-6 | AC | Least Privilege
AT-1 | AT | Policy and Procedures
AT-2 | AT | Literacy Training and Awareness
AU-1 | AU | Policy and Procedures
AU-2 | AU | Event Logging
AU-6 | AU | Audit Record Review, Analysis, and Reporting
CA-2 | CA | Control Assessments
CA-5 | CA | Plan of Action and Milestones
CA-6 | CA | Authorization
CA-7 | CA | Continuous Monitoring
CM-2 | CM | Baseline Configuration
CM-6 | CM | Configuration Settings
CM-8 | CM | System Component Inventory
CP-1 | CP | Policy and Procedures
CP-9 | CP | System Backup
IA-2 | IA | Identification and Authentication (Organizational Users)
IA-5 | IA | Authenticator Management
IR-1 | IR | Policy and Procedures
IR-4 | IR | Incident Handling
IR-6 | IR | Incident Reporting
MA-2 | MA | Controlled Maintenance
MP-2 | MP | Media Access
MP-6 | MP | Media Sanitization
PE-2 | PE | Physical Access Authorizations
PE-6 | PE | Monitoring Physical Access
PL-1 | PL | Policy and Procedures
PL-2 | PL | System Security and Privacy Plans
PM-9 | PM | Risk Management Strategy
PS-3 | PS | Personnel Screening
PS-4 | PS | Personnel Termination
PT-1 | PT | Policy and Procedures
PT-3 | PT | Personally Identifiable Information Processing Purposes
RA-3 | RA | Risk Assessment
RA-5 | RA | Vulnerability Monitoring and Scanning
SA-4 | SA | Acquisition Process
SA-9 | SA | External System Services
SC-7 | SC | Boundary Protection
SC-13 | SC | Cryptographic Protection
SI-2 | SI | Flaw Remediation
SI-4 | SI | System Monitoring
SR-2 | SR | Supply Chain Risk Management Plan
SR-6 | SR | Supplier Assessments and Reviews

## Template 5 - SAP Worksheet
Template 5 - Security Assessment Plan (SAP) Worksheet (Assess Step)
Define scope, methods, schedule and team for the control assessment before it begins. See Handbook Walkthrough E.
System Name | Case Management Portal (EXAMPLE)
System Categorization | Moderate (EXAMPLE)
Assessment Type | Initial assessment supporting new ATO (EXAMPLE)
Control Assessor / SCA (name, organization) | Independent Assessment Team, Agency Office of IG - organizationally separate from System Owner (EXAMPLE)
Is this a FedRAMP assessment requiring a 3PAO? | No - agency-internal RMF assessment (EXAMPLE)
Assessment Scope (controls/components included) | All Moderate baseline controls selected in Template 3, both system-specific and hybrid; common controls verified by reference to provider's assessment, not re-tested (EXAMPLE)
Assessment Methods | Examine (documents/artifacts), Interview (control owners/ISSO), Test (technical controls e.g. access enforcement, vulnerability scanning) (EXAMPLE)
Assessment Procedures Reference | SP 800-53A Rev 5 assessment procedures, tailored to selected controls (EXAMPLE)
Assessment Schedule (start / end) | 2026-08-01 to 2026-08-14 (EXAMPLE)
Rules of Engagement (for technical testing) | Vulnerability scans limited to non-production hours; no exploitation of production data; system owner notified 24 hrs before any active testing (EXAMPLE)
SAP Approved By | D. Whitfield, AO (EXAMPLE)
SAP Approval Date | 2026-07-20 (EXAMPLE)

## Template 6 - Control Assessment
Template 6 - Control Assessment Checklist (Assess Step)
Control-by-control test results organized by the 20 SP 800-53 families. See Handbook Walkthrough F.
Control ID | Family | Control Name | Assessment Procedure Summary | Evidence Examined | Result | Assessor | Date
AC-2 | AC | Account Management | Examine account management procedures; interview ISSO; test a sample of 10 accounts for timely provisioning/deprovisioning (EXAMPLE) | Account creation/termination logs Q2 2026; IAM configuration export; interview notes 2026-08-03 (EXAMPLE) | Satisfied | M. Chen | 2026-08-03
AC-1 | AC | Policy and Procedures | Confirm access control policy/procedures exist, are disseminated and reviewed on the defined cycle.
AC-2 | AC | Account Management | Test that accounts are provisioned, reviewed, and disabled/removed per defined conditions.
AC-3 | AC | Access Enforcement | Confirm the system enforces approved authorizations for logical access.
AC-6 | AC | Least Privilege | Confirm accounts/roles are restricted to the minimum access necessary.
AT-1 | AT | Policy and Procedures | Confirm awareness and training policy/procedures exist and are reviewed on schedule.
AT-2 | AT | Literacy Training and Awareness | Confirm all users complete security/privacy literacy training before access and periodically thereafter.
AU-1 | AU | Policy and Procedures | Confirm audit and accountability policy/procedures exist and are reviewed on schedule.
AU-2 | AU | Event Logging | Confirm the system identifies and logs the events required to support after-the-fact investigation.
AU-6 | AU | Audit Record Review, Analysis, and Reporting | Confirm audit logs are reviewed/analyzed at a defined frequency and findings reported.
CA-2 | CA | Control Assessments | Confirm assessments are conducted at the defined frequency using an approved assessment plan.
CA-5 | CA | Plan of Action and Milestones | Confirm a POA&M is developed and updated to track remediation of assessment findings.
CA-6 | CA | Authorization | Confirm an authorizing official has issued an authorization decision before operation.
CA-7 | CA | Continuous Monitoring | Confirm a system-level continuous monitoring strategy is implemented per the ConMon plan.
CM-2 | CM | Baseline Configuration | Confirm a current, documented, approved baseline configuration is maintained.
CM-6 | CM | Configuration Settings | Confirm configuration settings reflect the most restrictive mode consistent with operational need.
CM-8 | CM | System Component Inventory | Confirm an accurate, current inventory of system components is maintained.
CP-1 | CP | Policy and Procedures | Confirm contingency planning policy/procedures exist and are reviewed on schedule.
CP-9 | CP | System Backup | Confirm backups of user- and system-level information are conducted and tested.
IA-2 | IA | Identification and Authentication (Organizational Users) | Confirm the system uniquely identifies and authenticates organizational users.
IA-5 | IA | Authenticator Management | Confirm authenticators (passwords, tokens, certs) are managed per policy over their lifecycle.
IR-1 | IR | Policy and Procedures | Confirm incident response policy/procedures exist and are reviewed on schedule.
IR-4 | IR | Incident Handling | Confirm an incident handling capability covering preparation, detection, analysis, containment, recovery is implemented.
IR-6 | IR | Incident Reporting | Confirm incidents are reported to designated authorities within required timeframes.
MA-2 | MA | Controlled Maintenance | Confirm maintenance activities are scheduled, performed, and documented.
MP-2 | MP | Media Access | Confirm access to digital and non-digital media is restricted to authorized individuals.
MP-6 | MP | Media Sanitization | Confirm media is sanitized prior to disposal, release, or reuse.
PE-2 | PE | Physical Access Authorizations | Confirm a current list of personnel with authorized physical access is maintained.
PE-6 | PE | Monitoring Physical Access | Confirm physical access is monitored and unauthorized/suspicious access investigated.
PL-1 | PL | Policy and Procedures | Confirm planning policy/procedures exist and are reviewed on schedule.
PL-2 | PL | System Security and Privacy Plans | Confirm the SSP is developed, reviewed, approved and kept current.
PM-9 | PM | Risk Management Strategy | Confirm an organization-wide risk management strategy is documented and implemented.
PS-3 | PS | Personnel Screening | Confirm personnel are screened prior to authorizing access, and rescreened per conditions.
PS-4 | PS | Personnel Termination | Confirm access is disabled and credentials/property recovered upon termination.
PT-1 | PT | Policy and Procedures | Confirm PII processing and transparency policy/procedures exist and are reviewed on schedule.
PT-3 | PT | Personally Identifiable Information Processing Purposes | Confirm PII is processed only for identified, documented purposes.
RA-3 | RA | Risk Assessment | Confirm a risk assessment (including threat/vulnerability identification) is conducted and documented.
RA-5 | RA | Vulnerability Monitoring and Scanning | Confirm vulnerability scanning is performed at the defined frequency and findings remediated.
SA-4 | SA | Acquisition Process | Confirm security/privacy requirements are included in acquisition contracts.
SA-9 | SA | External System Services | Confirm external/cloud service providers meet required security and privacy requirements.
SC-7 | SC | Boundary Protection | Confirm the system monitors and controls communications at external/internal boundaries.
SC-13 | SC | Cryptographic Protection | Confirm cryptographic mechanisms are implemented per applicable law, policy and standards.
SI-2 | SI | Flaw Remediation | Confirm system flaws are identified, reported and corrected in a timely manner.
SI-4 | SI | System Monitoring | Confirm the system is monitored to detect attacks, indicators of compromise, and unauthorized use.
SR-2 | SR | Supply Chain Risk Management Plan | Confirm a supply chain risk management plan is developed and implemented.
SR-6 | SR | Supplier Assessments and Reviews | Confirm suppliers are assessed/reviewed against supply-chain risk criteria before and during use.

## Template 7 - Evidence Log
Template 7 - Evidence Log
Log every piece of evidence as you gather it during the assessment - do not reconstruct from memory later. See Handbook Walkthrough G.
Evidence ID | Date / Time | Source (Person / Document) | Control ID | Description of Evidence Examined | Supports | Assessor
EV-001 (EXAMPLE) | 2026-08-03 10:20 | Interview: P. Nakamura, ISSO | AC-2 | Walked through IAM provisioning workflow and reviewed Q2 2026 account audit export | Supports Satisfied | M. Chen

## Template 8 - POA&M
Template 8 - Plan of Action and Milestones (POA&M)
Tracks remediation of SAR-identified weaknesses; continues to be updated during Monitor. See Handbook Walkthrough H.
Weakness ID | Control ID | Weakness Description | Risk Rating | Mitigation / Corrective Action | Resources Required | Milestones / Dates | Status | Completion Date
POAM-001 | SI-2 | Critical vulnerability scan findings not remediated within the 30-day policy window on 4 of 12 sampled hosts (EXAMPLE) | Moderate | Implement automated patch management with enforced SLA and exception workflow | 0.5 FTE patch engineer; patch management tool license | M1: Tool procured 2026-09-01; M2: Enrolled all hosts 2026-09-30; M3: First full SLA-compliant cycle 2026-10-31 | Open

## Template 9 - SAR Summary
Template 9 - Security Assessment Report (SAR) Summary (Assess Step)
Summarize assessment results for inclusion in the authorization package. See Handbook Walkthrough I.
System Name
System Categorization
Assessment Dates
Control Assessor / SCA
Assessment Scope Summary
Total Controls Assessed
Controls Satisfied
Controls Other Than Satisfied
Summary of Significant Weaknesses (cross-reference POA&M IDs)
Assessor's Overall Risk Statement
Recommendation to AO (proceed to Authorize / remediate first)

## Template 10 - AO Decision
Template 10 - Authorization Decision Record (Authorize Step)
Records the Authorizing Official's non-delegable risk-acceptance decision. See Handbook Walkthrough J.
System Name | Case Management Portal (EXAMPLE)
System Categorization | Moderate (EXAMPLE)
Authorization Package Reviewed (SSP / SAR / POA&M / Exec Summary) | SSP v2.1, SAR dated 2026-08-14, POA&M v1.0 (3 open items), Executive Summary dated 2026-08-18 (EXAMPLE)
SAR Summary (cross-reference Template 9) | 40 of 43 assessed controls Satisfied; 3 Other Than Satisfied, all tracked in POA&M (EXAMPLE)
Residual Risk Summary | Residual risk assessed as Moderate; consistent with organizational risk tolerance given planned POA&M remediation (EXAMPLE)
AO Decision | Authorized with Conditions (EXAMPLE)
Terms and Conditions (if any) | POAM-001 remediated within 60 days; monthly POA&M status reporting to AO until closure (EXAMPLE)
Authorization Termination Date | 2029-08-18 (3-year cycle, superseded by ongoing authorization under ConMon where applicable) (EXAMPLE)
Authorizing Official Name | D. Whitfield, CISO (EXAMPLE)
AO Signature / Date | [signed] 2026-08-18 (EXAMPLE)
AO Designated Representative (if package prepared by AODR) | K. Osei - note: AODR may coordinate the package but cannot render the risk-acceptance decision itself (EXAMPLE)

## Template 11 - ConMon Schedule
Template 11 - Continuous Monitoring (ConMon) Schedule (Monitor Step)
Ongoing monitoring cadence per control/family - supports ongoing authorization rather than a fixed reauthorization cycle. See Handbook Walkthrough K.
Family | Family Name (Reference) | Monitoring Method | Frequency | Responsible Party | Last Reviewed / Next Due
RA | Risk Assessment | Automated vulnerability scanning + manual review of scan trends (EXAMPLE) | Weekly (scan); Quarterly (trend review) | P. Nakamura (ISSO) | 2026-08-10 / 2026-08-17
AC | Access Control
AT | Awareness and Training
AU | Audit and Accountability
CA | Assessment, Authorization, and Monitoring
CM | Configuration Management
CP | Contingency Planning
IA | Identification and Authentication
IR | Incident Response
MA | Maintenance
MP | Media Protection
PE | Physical and Environmental Protection
PL | Planning
PM | Program Management
PS | Personnel Security
PT | PII Processing and Transparency
RA | Risk Assessment
SA | System and Services Acquisition
SC | System and Communications Protection
SI | System and Information Integrity
SR | Supply Chain Risk Management